## Test cases
Product Name |  |  | Ajkerdeal | TC Start Date | 2022-08-11 | TC Execution Start Date | 2022-08-11 | TEST CASES |  | List of the emprovement Scope
Module Name |  |  | User Management | TC End date | 2022-11-11 | TC Execution End Date | 2022-11-11 | PASS | 53 | Name field should take valid formate
Developer Name |  |  | Mr.XX | Test Case Developed By | Mst.Tania khatun |  |  | FAIL | 11 | System should be sent OTP code
|  |  |  | Test Case Reviewed By | N/A | Performance (tested) |  | Not Executed | 0 | Marchent corner Password field must be Improve
Test Executed By |  |  | Mst.Tania khatun
[8 empty] | TOTAL | 64
Test Case ID | Module | Feature | Test Case | Test Steps | Test Data | Expected Result | Actual Result | Bug Screenshots | Status | Remarks
TC001 | User Management | Registration | Verifying whether the Registration page appears | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on register section 3. A new page appears with having Register andregistrationbuttons. Click on the "Register" button. | N/A | A registration UI should apear | Registration page showing |  | Passed
TC002 |  |  | Check the Language column and select the language what you want to use. | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on register section | N/A | The expected language should be shown in all sections. | If select english at first show 404 error massage and registration page show on bangla. | mistake language | Failed
TC003 |  |  | Try to registration in without Name/Email/Phone Number and Password | 1. Browse the URL (https://ajkerdeal.com/) 2. Keep the Email box and password blank 3. Click on the Register button | Name/Email/Phone number = Null Password = Null | User should not be able to registration and there should be an alert such as "Please enter Name,email or phone number" | Not able to registration and the alert message shows properly |  | Passed
TC004 |  |  | Try to register without Name/Email/Phone Number with Password value | 1. Browse the URL (https://ajkerdeal.com/) 2. Keep the Email box blank and put valid password 3. Click on the Register button | Name/Email/Phone number = Null Password = acD@585197 | User should not be able to registration and there should be an alert such as "Please enter valid email or phone number" | Not able to registration and the alert message shows properly |  | Passed
TC005 |  |  | Try to registration with valid Email but empty Password | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the valid Email in the box and keep password empty 3. Click on the Register button | Email = *****@gmail.com Password = Null | User should not be able to registration and there should be an alert such as "Please enter password" | Not able to registration and the alert message shows properly |  | Passed
TC006 |  |  | Try to registration without Name valid Phone Number with a valid Password | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the valid Email and password in the box and keepName empty 3. Click on the Register button | Name: Null Phone:017865*******88 Password:12345 | User should not be able to registration and there should be an alert such as "Please enter Name" | Not able to registration and the alert message shows properly |  | passed
TC007 |  |  | Try to registration in name field with numeric value | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the name in numeric value 3. Click on the Register button | Name:354757656 | User should not be able to registration and there should be an alert such as "Please enter Proper Name" | able to registration | Name issu | Failed
TC008 |  |  | Try to registration Phone number value in alphabet | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the field in letter 3. Click on the Register button | Name:Tania Phone:jhndfkkdjfkdfjgkjgj Password:12345 | User should not be able to registration and there should be an alert such as "Please enter Proper Name" | Not able to registration and the alert message shows properly |  | Passed
TC009 |  |  | Try to registration Phone field with special characters | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the field with special carecter 3. Click on the Register button | Name:Tania Phone:@#$%*&%$#@ Password:12345 Retype Pasword: 1234 | User should not be able to registration and there should be an alert such as "Please enter Proper Name" | Not able to registration and the alert message shows properly |  | Passed |  | name isu
TC010 |  |  | Try to registration without retype password | 1. Browse the url "https://ajkerdeal.com" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button | Name:Tania Phone:0134578********8 Password:12345 Retype Pasword: Null | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC011 |  |  | Try to Registration Phone field with alpha-numeric input | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the phone field with alpha-numeric 3. Click on the Register butto | Phone: tania12345 | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC012 |  |  | Try to registration Phone number field with up 10 digits | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the number 4. Click on the Registration button | Phone:019345678 | User should not be able to registration and there should be an alert such as "Please fill retype phone number" | Not able to registration and the alert message shows properly |  | Passed
TC013 |  |  | Try to registration Phone number field with space in between valid input | 1. Browse the URL ("https://ajkerdeal.com/") 2. Put the number with space 4. Click on the Registration butto | Phone:01934 56789 | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC014 |  |  | Tey to registration Phone field with already existed phone number | 1. Go to url ""https://ajkerdeal.com/" 2. Click on "registration" button. 3. Put test data on phone field 4. Click on registration button | phone:01723****14 | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC015 |  |  | Try to registration Password field with alphabets | 1. Go to url "https://ajkerdeal.com" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password: taniajkjkjf | User should be able to registration | able to registration |  | Passed
TC016 |  |  | Try to registration password does not take more than 20 digit | 1. Go to url "https://ajkerdeal.com" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password: ta@234567890167890987654321 | User should not be able to registration | System take mora then 20 digit and User able to registration |  | Failed
TC017 |  |  | Try to registration Password field with numbers | 1. Go to url "https://ajkerdeal.com" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password:6236484787 | User should be able to registration | User able to registration |  | Passed
TC018 |  |  | Try to registration Password field with space inputs | 1. Go to url "https://ajkerdeal.com" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password:123 678 | User should not be able to register | User able to registration |  | Failed
TC019 |  | login | Try to login Email field with empty input | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.keep mail field emty 4.click on login button | mail: Null | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC020 |  |  | Try to login Email field with invalid format | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put mail invalid formate 4.click on login button | Mail :(*&^%Gghhjhi@gmail.com | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC021 |  |  | Try to login Email field with numbers | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.put mail only number 4.click on login button | Mail: 089849783458 | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC022 |  |  | Try to login Email field with only alphabets | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put mail formate only alphabet 4.click on login button | Mail:kjhfsdjhkdfjgkdfj | User should not be able to login | Not able to login the alert message shows properly |  | Passed
TC023 |  |  | Try to login Email field with already existed mail id | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put mail invalid formate 4.click on login button | Mail:tania.cse2987@gmail.com | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC024 |  |  | Try to login Email field without " @ " sign | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put mail without @ sign 4.click on login button | Mail: tania.vcdjfhj.gmail.com | User should not be able to login | Not able to login the alert message shows properly |  | Passed
TC025 |  |  | Try to login Password field empty | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Keep password field emty 4.click on login button | mail :tsghbgjsf.@gmail.com password:Null | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC026 |  |  | Try to login Password field with alphabets | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.put password formate only alphabet 4.click on login button | Password:taniagyt | User should be able to login | able to login |  | Passed
TC027 |  |  | Try to login Password field with special characters | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put password formate with special carecter 4.click on login button | Password:taniagyt$#@ | User should be able to login | able to login |  | Passed
TC028 |  |  | Password field with space inputs | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put password with space 4.click on login button | Password:taniagyt *** | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC029 |  |  | Try to login Maximum password length 11 digit | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put password 4.click on login button | password :12345678900 | User should not be able to login with morethan 11 carecter | User use more than 11 character |  | Failed
TC030 |  |  | Try to login valid email but invalid password | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put invalid password and invalid email 4.click on login button | Email:taniahjfhr@gmail.com password:%^&*($#@@ | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC031 |  |  | Try to login with valid email and valid password | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.Put valid password and valid email 4.click on login button | Email:taniahjfhr@gmail.com password: tania56789 | User should be able to login | user login properly |  | Passed
TC032 |  |  | Try to login without email and password | 1. Go to url "https://ajkerdeal.com/" 2. Go to "login" menu and click on login 3.kepp password and email emty 4.click on login button | Email:Null password:Null | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC033 |  | Order | Verify All product menu working | 1.Brows Url 2.click one by one product menu |  | Produt menu should be Working Fine | Product menu working fine |  | Passed
TC034 |  |  | Verify that user should be able to order the product with proper information and step | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | user should order properly | user order properly |  | Passed
TC035 |  |  | Verify that on the product page, the user can select the desired attribute of the product e.g. size, color, etc. | 1.Click product Images 2.Select size |  | User shoud be able select Size with radio button | User able to select size properly |  | Passed
TC036 |  |  | Verify that the user can add to cart one or more products. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option on card 8.Selact delivery system 9. Click order confrom |  | user should order properlywith cart | user order properly |  | Passed
TC037 |  |  | verify user select size more than one at a time | 1.Click product Images 2.Select size |  | User should not selet more than size ta a time | User not select more than one size |  | Passed
TC038 |  |  | Verify that users can add more products to the list | 1.Click product Images 2.Select size 3. Again go home and select product |  | User should be add more than one product | User able to add more product properly |  | Passed
TC039 |  |  | Verify that the user cannot add more than the available inventory of the product. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | User should not be add more than one product | User able to add more product properly |  | Failed
TC040 |  |  | Verify that the limit to the number of products a user can by is working | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | User should br order product number of limit | User can order product number of limit |  | Passed
TC041 |  |  | Verify that the different pre-paid methods of payments are working fine. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | Pre-paid mathod shoud working fine | Prepaid mathod working fine |  | Passed
TC042 |  |  | Verify that product return functionality works fine. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact return option 9. Click return confrom |  | Product return function should working fine | Product return function working well |  | Passed
TC043 |  |  | Verify that user should be able to return the order after delivery of order. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact return option 9. Click return confrom |  | should be able to return the order after delivery of order. | able to return the order after delivery of order. |  | passed
TC044 |  |  | Verify that user should be able to exchange the order from My orders page. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact exchange option 9.confrom exchange |  | should be able to exchange the order from My orders page | able to exchange the order from My orders pag |  | Passed
TC045 |  |  | Verify the searching work properly | 1.go home page 2.write product name or category 3.click search button |  | user should be search product properly | user can search product properly |  | Passed
TC046 |  |  | Verify that the Cash on Delivery option of working fine. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.click cash on delivery option |  | Delivery option should be work properly | Delivery option working properly |  | Passed
TC047 |  |  | verify order product without Address | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town |  | order product without Address should not working | not working deliver system show an error massage |  | Passed
TC048 |  |  | verify order with cash on delivery | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town |  | Order sucessfully but not add del |  |  | Passed
TC049 |  | Payment | Verify Payment with Bkash | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on bkash option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC050 |  |  | Verify Payment with Merchant Account | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on marchent account option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC051 |  |  | Verify Payment with Visa Card | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on Visa card Option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC052 |  |  | Verify Payment with Amex card | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on Visa card Option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC053 |  |  | Verify cash on delivery | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on Visa card Option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC054 |  | Marchant Corner | Try to Registration without Buisness Name, phone number and facebook link | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4. click registration button without value |  | User should not be able toregistration and there should be an alert such as "Please enter Name, phone number". | Not able to registration and the alert message shows properly |  | Passed
TC055 |  |  | Try to Registration Buisness Name, phone number and Wiithout facebook link field emty | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4. Fill up Buisness name and phone number 5.click registration button without value | Buisness: Name: Jewelry home Phone:01376874638 facebook link : Null | User should not be able toregistration and there should be an alert such as "Please enter facebook link " | Not able to registration and the alert message shows properly |  | Passed
TC056 |  |  | Try to Registration without Buisness Name | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4. Fill option without Buisness name 5.click registration button without value | Buisness: Name: Null Phone:01376874638 facebook link : https://www.facebook.com/ | User should not be able toregistration and there should be an alert such as "Please enter facebook link " | Not able to registration and the alert message shows properly |  | Passed
TC057 |  |  | Try to registration invalid facebook link | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4. put invalid facebook link 5.click registration button without value | Buisness: Name: Jwelary Home Phone:01376874638 facebook link : 63578648935 | User should not be able toregistration and there should be an alert such as "Please enter facebook link " | User able to registration | facebook link | Failed | 0
TC058 |  |  | Try to registration without facebook link | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4.click registration button without value | Buisness: Name: Jwelary Home Phone:01376874638 facebook link : Null | User should not be able toregistration and there should be an alert such as "Please enter facebook link " | Not able to registration and the alert message shows properly |  | Passed
TC059 |  |  | Fill Buisness name only alphabetic value | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4.fill up option 5.click registration button without value | Buisness: Name: 65743564658 Phone:01376874638 facebook link : https://www.facebook.com/ | User should not be able toregistration and there should be an alert such as "Please enter facebook link " | User able to registration | invalid name | Failed
TC060 |  |  | Try to registration without phone number | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4.fill up option 5.click registration button without value | Buisness: Name: 65743564658 Phone:Null facebook link : https://www.facebook.com/ | User should not be able to registration and there should be an alert such as "Please enter phone number " | Not able to registration and the alert message shows properly |  | Passed
TC061 |  |  | Try to registration with OTP Code | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4.fill up option 5.click registration button without value | Buisness: Name: 65743564658 Phone:01516144938 facebook link : https://www.facebook.com/ | User be able toregistration with OTP code. | System Doesn't provide OTP code |  | Failed |  |  | 1. Name field should take only text input or combination of text, numeric.
TC062 |  |  | Try to registration with proper information | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4.fill up option 5.click registration button without value | Buisness: Name: 65743564658 Phone:01516144938 facebook link : https://www.facebook.com/ | User should be able to registration . | User should be able to registration . |  | Passed |  |  | 2. Tab button should work for navigating for every field, checkbox, hyperlink and button
TC063 |  | Forget Password | Try to reset password from option and puting phone number | 1.Brows Url 2.click on login option 3.Fill email Option 4. click forget password button |  | System should be provide OTP code | System Doesn't provide OTP code |  | Failed
TC064 |  |  | Try to reset password from option and puting phone number | 1.Brows Url 2.click on login option 3.Fill email Option 4. click forget password button |  | System should be provide OTP code | System Doesn't provide OTP code |  | Failed

## Test report
Test Case Report
Project Name - | Ajkerdeal.com
Module Name - | User Management |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 53 | PASS
Written By | Tania Khatun |  |  |  |  | 11 | FAIL
Executed By | Tania Khatun |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | [5 empty] | 0 | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 53 | 11 | 0 | 0 | 64
Grand Total | 53 | 11 | 0 | 0 | 64
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting |  |  |  | Bug Report
TC:02 |  |  |  | TC:07
Issue:Language Option not working |  |  |  | Issue:Taken unstructured name
Reproducing Steps: |  |  |  | Reproducing Steps:
1.Brows Url |  |  |  | 1.Brows Url
2.Select language Option |  |  |  | 2.click on registration option
3.Click on language Name |  |  |  | 3.Fillup name option
3.keep password
Env: |  |  |  | 4.Click on register button
Module:Registration |  |  |  | Env:
Severity:P1 |  |  |  | Module:Registration
Screenvideo: 404 error |  |  |  | Severity:P3
Responsible QA:Tania |  |  |  | Video: | Name Issu
Responsible QA:Tania
| Bug Report |  |  |  |  | Bug Report
| TC:07 |  |  |  |  | TC:57
| Issue:Taken unstructured name |  |  |  |  | Issue: invalid Facebook link
| Reproducing Steps: |  |  |  |  | Reproducing Steps:
| 1.Brows Url |  |  |  |  | 1.Brows Url
| 2.click on registration option |  |  |  |  | 2.click On merchant Corner
| 3.Fillup name option |  |  |  |  | 3.Fillup name option
| 3.keep password |  |  |  |  | 3.keep phone number |  | and invalid facebbok link
| 4.Click on register button |  |  |  |  | 4.Click on register button
| Env: |  |  |  |  | Env:
| Module:Registration |  |  |  |  | Module:Registration | Merchant Corner
| Severity:P3 |  |  |  |  | Severity:P3 | P1
| Screen recoder |  | Password |  |  | Screen recoder |  | Link
| Responsible QA:Tania |  |  |  |  | Responsible QA:Tania
Bug Report
TC:57
| Issue: invalid name |  | Name
Reproducing Steps:
1.Brows Url
2.click On merchant Corner
3.keep invalid name formate
4.Click on register button
Env:
| Module:Registration | Merchant Corner
| Severity:P3 | P1
| Screen recoder |  | Link
Responsible QA:Tania

## Test matrix
Test Metrics
SL NO | Metrics | Description | Result
1 | Percentage of test cases Executed | (No.of Test Cases Executed / Total no.of Test Cases Written)*100 | (64/64)*100 = 100
2 | Percentage of test cases not Executed | (No.of Test Cases not Executed / Total no.of Test Cases Executed)*100 | (0/64)*100 = 0
3 | Percentage of test cases Passed | (No.of Test Cases Passed / Total no.of Test Cases Executed)*100 | (53/64)*100 = 82.41
4 | Percentage of test cases Failed | (No.of Test Cases Failed / Total no.of Test Cases Executed)*100 | (11/64)*100 = 17.19
5 | Percentage of test cases Blocked | (No.of Test Cases blocked / Total no.of Test Cases Executed)*100 | (0/64)8100 = 0
6 | Defect Density | No. of defect found / Size (No.of requirments) | N/A
7 | Defect Removal Efficiency(DRE) | (Fixed Defects / (Fixed Defects + Missed Defects))*100 | N/A
8 | Defect Leakage | (No of Defects found in UAT / No.of Defects found in Testing)*100 | N/A
9 | Defect rejection Ratio | (No.of Defects Rejected / Total no.of Defects raised)*100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No.Of complaints per Period of Time | N/A